## Planning
Live Oak International 2018 Tasks
Date | Task | Responsible Party | Status
| Judges/Officials hired | Damien Guthrie
| Judges travel arrangements | Damien Guthrie
| Judges Housing | Damien Guthrie
| Hotel rooms booked | Damien Guthrie
| Judges Transportation | Damien Guthrie
| Vets hired | Damien Guthrie
| Stewards hired | Damien Guthrie
| Dressage Rings Cleaned | Mitja and Crew
| Cones Cleaned | Mitja and Crew | ??
2018-03-01 | Bring Driving Office Equipment to Show Trailer | Mitja/Damien
| Insurance secured | Damien Guthrie
| Insurance sent to USEF | Damien Guthrie
| Ribbons Purchased | Damien Guthrie
| Trophies Ordered | Damien Guthrie
| Radios orderd | Ellen Ettenger | Complete
| Volunteers secured | Julia
| Port O Lets Ordered | Damien Guthrie
| Program | Damien Guthrie
| Ring and Obstacle Decorations | Damien Guthrie
| Blacksmith Confirmed for Saturday | Damien Guthrie
| Stable Manager Confirmed | Damien Guthrie
| Golf Carts and Gators | Damien Guthrie
| Sponsors Tent | Damien Guthrie
| Vendors | Damien Guthrie
| EMT's Confirmed | Damien Guthrie
| USEF Measuring Stick Ordered | Ellen | Complete
| Officials Name Badges W/radio channels | Janet Hamilton
| Bridle Numbers | Janet Hamilton
| Prepare Preliminary Schedule of Events | Janet Hamilton
| Prepare Stable Chart | Janet Hamilton
| Competitor Numbers | Janet Hamilton | Damien Ordered
As soon as you arrive | Inventory Office Equipment | Janet Hamilton
Set Up Office
Day 1 | Prepare Accident Plan | JH/EE/DG | After it is prepared and approved, give one to each driving official
Monday | Prepare Important Phone Numbers | JH/EE/DG | After it is prepared and approved, give one to each driving official
| Prepare Final Schedule of Events | JH/EE/DG/Jenz | After it is prepared and approved, give one to each driving official
| Officials Packets | Janet Hamilton
| Competitor Packets | Janet Hamilton
| Get Obs Maps and Course Maps from CD | Ellen Ettenger
| Prepare Preliminary Horse Inspection Order | JH/EE/Jenz/DG/CW
| Prepare Preliminary Schedule for Dressage | JH/EE/Jenz/DG/CW
| Copy Dressage Tests | Janet Hamilton | Need Order of Go from Jenz for correct count
| Prepare Dressage Boards | Janet Hamilton
Day 2 | Officials Arrive Tuesday Evening |  | Confirmed w/DG
Tuesday | Finish anything that did not get done from Monday | JH
| Make sure Bridle Numbers are in Order | JH
| Make copies of course maps and obstacle maps for course inspection on wedneday | JH
9:00 | Stabling Open |  | Omnibus does not give time
12:00 | Show Office Open | JH | Omnibus does not give a time, I would say open at 12 and have packets available. JH should confirm this with DG and CW
12:00 | Packets Available | JH
Day 3
Wednesday 9 AM | Officials Course Inspection | CD/TD/POJ | Confirm Time
13:00 | Pony Measurement | TD/FEI Vet | Confirm Time
14:00 | FEI (CAI) Horse Inspection | TD/FEI Vet/Treating Vet/Jury | Confirm Time
Day 4 | Dressage FEI
Thursday 8:30 AM | Competition Arena
16:30 | Course Inspection for Driving Competitors
18:30 | Competitor Social and Briefing
| Prepare Paperwork for Intermediate Dressage on Friday | JH | If enough clipboards, you can do this all at the same time on Monday. If not, then you have to wait for the boards that are being used to come back
| Start prepping paperwork for marathon | JH
Day 5 | Dressage INT
Friday 8:30 AM | Finish Boards for Marathon | JH
Day 6 | Marathon
Saturday 8 AM | Prep Boards for Cones | JH
| Prep for Awards?? | JH/Susan Gilliland?
Day 7 | Cones
Sunday 8 AM | Pack Up Office | JH
Kathy will help

## Office Equipment Checklist
Pens
Rubber Bands
Binder Clips
Page Protectors
Laminating Machine
Laminating Sheets
Bins for Judges
Legal Paper - 3 reams, 3 different colors, one being white
Letter Paper Pastel Colors - at least 6 reams of different colors
Letter Paper - White - 1 Case of at least 5 reams
Card Stock White
Card Stock Green
Scissors
Scotch Tape
Duct Tape
Push Pins
Stapler (at least 2)
Staples
Staple Gun
Staples for Staple Gun
Paper Cutter
Label Maker
Refills for Label Maker
9 X 12 Envelopes for Competitor Packets
Folders for Judges
Gallon Ziploc Bags for Passports
2.5 Gallon Ziploc Bags for Volunteer Paperwork
Rubber Gloves for FEI Steward

## Officials Packet
Schedule of Events
Officals Schedule of Events
Horse Inspection Order
Copies of Course Maps
Copies of Obstale Maps
Accident Prep Plan
Name Badges w/Radio Channels
Important Numbers
Dressage Schedule if Done
Stable Chart

## Horse Inspection Board Setup
10 Clipboards
Order of Go
Pens

## Dressage Board Setup
Judge at C | Judge at R | Judge at S | Judge at V | Judge at P
Red Dots | Pens, no Pencils | Pens, no Pencils | Pens, no Pencils | Pens, no Pencils
Pens, no Pencils | 2 Orders of Go | 2 Orders of Go | 2 Orders of Go | 2 Orders of Go
Bell or Whistle | Dressage Tests in Order of how they will be driven, including 2 extra of each test | Dressage Tests in Order of how they will be driven, including 2 extra of each test | Dressage Tests in Order of how they will be driven, including 2 extra of each test | Dressage Tests in Order of how they will be driven, including 2 extra of each test
2 Orders of Go | Breaker Page | Breaker Page | Breaker Page | Breaker Page
Dressage Tests in Order of how they will be driven, including 2 extra of each test | Dressage Scribe Instructions | Dressage Scribe Instructions | Dressage Scribe Instructions | Dressage Scribe Instructions
Breaker Page | Radio | Radio | Radio | Radio
Dressage Scribe Instructions
Radio
Dressage Gate | Dressage Warm Up | FEI Steward | Wheel Measurement
2 Orders of Go | 2 Orders of Go | 2 Orders of Go | 2 Orders of Go
Pens | Pens | Pens | Wheel Measurement Sheet
Radio | Radio | Radio
Copy of Declarations

## Marathon Board Setup
OBSTACLES |  | SECTIONS |  |  |  | VET BOX | 2 Complete Sets, 1 for End of Transer, 1 for End of B
Board #1 | Observer/Scribe | Start A | End A | Start Transfer | End Transfer | Board #1 | Board #2
Observer Instructions |  | Order of Go | Order of Go | Order of Go | Order of Go | Vet Box Timer Sheets | T,P,R Sheets
Obstacle Sheets (5 more than they need as extras) |  | Green Cards | Pens | Pens | Pens | Stopwatches (3) | Singles, Pairs and 4's
Red Dots |  | Safety Checklists | Back Up Sheet | Back Up Sheet | Back Up Sheet | Passing Time | Stopwatches (3)
Red Dot Form |  | Pens | Setion Timer Instructions | Setion Timer Instructions | Setion Timer Instructions | Pens | Pens
What to do when the day is over form |  | Back Up Sheet | Timing Clock | Timing Clock | Timing Clock
2 Order of Go |  | Setion Timer Instructions | Radio | Radio | Radio | Board #3 for FEI Steward
|  | Timing Clock |  |  |  | Wheel Measurement Sheet | Put a couple of extra boards in with the passing times on for whoever wants it
Board #2 | Back Up Timer | Radio |  |  |  | Passing Time
Timer Instruction Sheet
Radio Protocol Sheet |  | Start B | End B
Back Up Timer Sheets |  | Order of Go | Order of Go
2 Order of Go |  | Pens | Pens
|  | Back Up Sheet | Back Up Sheet
Board #3 | Hold Up Timer | Setion Timer Instructions | Setion Timer Instructions
Hold Up Instruction Sheet |  | Timing Clock | Timing Clock
2 Orders of Go |  | Passing Time | Radio
Radio
Put these 3 Boards in a large 2.5 Gallon Ziploc Packet with the following
Whistle
At least 2 stopwatches, 3 preferably
Pens (no pencils)
Radio

## Cones Setup
Judge 1 - 5 | Cones Steward
Course Map | Course Map 2 or 3
Times Allowed | Time Allowed
Order of Go | Order of Go
Bell/Whistle/Signal | Radio
Radio - 1 for each
Cones Warm Up
Cones Scribe | Order of Go
Cones Score Sheets | Radio
Order of Go
Course Map | Cones Gate
Time Allowed | Order of Go
Radio
Cones Back Up Timer
Back Up Timer Sheet | FEI Steward
Order of Go | Wheel Measurement Sheets
Order of Go
Cone Setters
Radio